## Cover
Honda Plan

## Change
Change history
# | Creator | Version | Date | Change contents
1 | Nguyen Hoang Viet | 1 | 3-thg 06- 2024 | Create new estimation
2
3
4
5
6
7

## Estimation
Detail Coding Estimation
Fucntion Information |  |  |  |  | Option-1 Est (MD) | Plan |  | Actual |  | Status | Note
No | Category | Person In Charge | Role | To Do List |  | Start date | End date | Start date | End date
1 | Nghiên cứu yêu cầu bài toán (Requirement) | GROUP 6 |  |  | 1 |  |  |  |  | 100%
|  | DuongTH |  | Tìm hiểu slide 4.9 Lab 4-Introduce students to data science tools. Perform basic operations on data 1.ppt | 1 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100%
|  | DuongTH |  | Tìm hiểu 2 file .csv | 2 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 100%
2 | Xử lý, dọn dẹp data (Data Cleaning) | GROUP 6 |  |  | 2 |  |  |  |  | 100%
|  | VietNH |  | Xử lý data | 1 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 100%
|  | VietNH |  | Tìm hiểu về IBM Waston Studio | 1 | 2024-06-04 | 2024-06-05 | 2024-06-04 | 2024-06-05 | 100%
3 | Nghiên cứu mô hình và đánh giá (Model traning & Evaluating) | GROUP 6 |  |  | 2 |  |  |  |  | 90%
|  | DuongTH |  | Xây dựng model và tham khảo. | 2 | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 | 90%
|  | DuongTH |  | Đánh giá model.. | 2 | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 | 90%
4 | Triển khai (Deploy) | GROUP 6 |  |  | 2 |  |  |  |  | 90%
|  | VietNH |  | Triển khai model trên một example web app | 2 | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-06-08 | 90%
5 | Kiểm tra | GROUP 6 |  |  | 1 |  |  |  |  | 100%
|  | DuongTH |  | Họp và thuyết trình thử | 1 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 100%
Total Man Days |  |  |  |  | 7 | [5 empty] | MD
[5 empty] | 0.35 | [5 empty] | MM
[5 empty] | 0.385 | [5 empty] | MM + 10% (PM)